## Consolidated Estimate
Task | Time Est. | Assignee | Front End/Back End | Notes
Connect Login DB with Spotify OAuth | 1 hour | Chris | Back End
Design/write login page w/spotify OAuth and app description | 2.5 hours | Chris | Front End
Write a list of pre-defined questions to find user interests | .5 hours | Manuela | N/A
Design a page where a user can respond to these questions | 2 hours | James | Front End
Create API calls to receive a POST of all these responses | 1.5 hours | Manuela | Back End
Create API call to parse the responses and another to POST to ChatGPT | 1 hour | Manuela | Back End
Create API call to parse ChatGPT response to get individual song titles | 3.5 hours | Chris/Manuela | Back End
Create API call to create Spotify Playlist | 1.5 hour | Chris/Manuela/James | Back End
Create API call to DallE to create image | 1 hour | James | Back End
Design/write a page where the new Spotify playlist is embedded and presented to the user | 3 hours | James | Front End
Create logout functionality within the web app | 1 hour | Manuela | Both
Create a login database | 1 hour | Chris | Back End
20 Hours

## Chris
Task | Time Est. | Assignee | Front End/Back End | Notes
Connect Login DB with Spotify OAuth | 1 hour | Chris | Back End
Design/write login page w/spotify OAuth and app description | 2.5 hours | Chris | Front End
Create a login database | 1 hour | Chris | Back End

## Manuela
Task | Time Est. | Assignee | Front End/Back End | Notes
Write a list of pre-defined questions to find user interests | 15 minutes | Manuela | N/A
Create API calls to receive a POST of all these responses | 1.5 hours | Manuela | Back End
Create API call to parse the responses and another to POST to ChatGPT | 1 hour | Manuela | Back End
Create logout functionality within the web app | 1 hour | Manuela | Both

## James
Task | Time Est. | Assignee | Front End/Back End | Notes
Design a page where a user can respond to these questions | 2 hours | James | Front End
Create API call to DallE to create image | 1 hour | James | Back End
Design/write a page where the new Spotify playlist is embedded and presented to the user | 3 hours | James | Front End